## Start here
OKR spreadsheet template
Track objectives, key results and weekly check-ins in one file. Rows marked (example) are there to show how it works: delete them when you add your own.
How to start
1. Settings: type your cycle start and end dates. Until you do, the file uses the current quarter.
2. OKRs: one row per key result. Fill in team, objective, key result, a short KR ID, one owner, a start and a target value. The gray columns fill themselves. Rows 2 to 31 are ready; for more, select the gray cells of the last row and drag them down.
3. Check-ins: every week, each owner adds a new row per key result (date, KR ID, new value, health, one-line comment). Add rows at the bottom and never edit old ones: the newest row is the current value.
4. Dashboard: column A lists the objectives from the OKRs tab by itself, up to 10, so don't type in it. Start the weekly review with stale key results and objectives behind pace.
5. Share the file with edit access for owners, and protect the gray columns so nobody types over a formula.
Health
On track: the key result will hit its target at this pace
At risk: it may miss without a change
Behind: it will miss without help
No status: no check-in yet
A key result turns stale (orange row on the OKRs tab) when it has had no check-in for longer than Settings!B3 days.
Excel 2016 or 2019 (no XLOOKUP)?
OKRs!H2: =IF(D2="","",IFERROR(LOOKUP(2,1/('Check-ins'!$B$2:$B$500=D2),'Check-ins'!$C$2:$C$500),F2)) then fill it down.
OKRs!J2: =IF(D2="","",IFERROR(LOOKUP(2,1/('Check-ins'!$B$2:$B$500=D2),'Check-ins'!$D$2:$D$500),"No status")) then fill it down.
OKRs!K2: =IF(D2="","",IFERROR(LOOKUP(2,1/('Check-ins'!$B$2:$B$500=D2),'Check-ins'!$A$2:$A$500),"")) then fill it down.
Made by the Effortbox team · effortbox.com
Setup guide and weekly routine: effortbox.com/blog/okr-spreadsheet

## Dashboard
OKR dashboard
Cycle
Days left
Cycle elapsed
Key results
On track
At risk
Behind
No status
Stale (no recent check-in)
Objective | Progress | Progress bar | At risk or behind | Gap to pace
Gap to pace = objective progress minus the share of the cycle that has passed. Negative means behind pace.

## OKRs
Team | Objective | Key result | KR ID | Owner | Start | Target | Current | Progress | Health | Last check-in | Days since check-in | Progress bar
Sales | Win more mid-market deals (example) | Raise demo-to-close rate from 18% to 25% | S-1 | Dana | 18 | 25
Sales | Win more mid-market deals (example) | Cut first-response time from 72 to 12 hours | S-2 | Lee | 72 | 12
Sales | Win more mid-market deals (example) | Sign 5 new reseller partners | S-3 | Dana | 0 | 5
Product | Make onboarding self-serve (example) | Launch the in-app setup checklist | P-1 | Ana | 0 | 1
Product | Make onboarding self-serve (example) | Raise week-1 activation from 35% to 50% | P-2 | Omar | 35 | 50
Customer Success | Keep our best customers (example) | Cut monthly churn from 3% to 2% | C-1 | Mia | 3 | 2
Customer Success | Keep our best customers (example) | Hold quarterly reviews with all 20 top accounts | C-2 | Mia | 0 | 20
Formulas:
Days since check-in = IF([KR ID]="","",TODAY()-IF([Last check-in]="",Settings!$B1,[Last check-in]))

## Check-ins
Date | KR ID | Value | Health | Comment | Entered by
| S-1 | 19.5 | On track | Example: two demos closed this week | Dana
| S-2 | 54 | On track | Example: added a second person to the inbox rota | Lee
| S-3 | 1 | On track | Example: first reseller signed; three more in legal | Dana
| S-1 | 21 | On track | Example: pipeline review done; next, two proposals | Dana
| S-2 | 41 | On track | Example: auto-triage rules live for the top 5 topics | Lee
| P-2 | 38 | Behind | Example: the new welcome email didn't move activation | Omar
| C-1 | 2.8 | On track | Example: two at-risk accounts saved by early calls | Mia
| S-1 | 21.5 | At risk | Example: two deals slipped to next quarter | Dana
| S-2 | 30 | On track | Example: weekend shift started; queue under 30 hours | Lee
| P-1 | 0 | At risk | Example: design done; build slipped a week | Ana
| P-2 | 39 | Behind | Example: testing a shorter setup flow next week | Omar
| C-1 | 2.6 | On track | Example: churn interviews scheduled with 6 accounts | Mia

## Settings
Cycle start |  | Formula: the first day of the current quarter. Type your own date over it.
Cycle end |  | Formula: the last day of that quarter. Type your own date over it.
Stale after (days) | 7 | 7 for weekly check-ins, 14 for every two weeks.
Health options
On track |  | The Health drop-down on the Check-ins tab reads this list.
At risk
Behind